## README
Pilot Implementation Work Plan — Agentic Target Modeling Solution
Scope | Pilot only, per Pilot Implementation Blueprint v0.1 (companion: Architecture Design v0.2). Read-only, recommendation-only pilot on Databricks: one source product/module/version, one domain/LOB.
Structure | Work Plan sheet expands the blueprint's 5 work packages into sequenced tasks with owners, dependencies, deliverables and exit criteria. Rows highlighted in red are stage gates.
No dates | Durations/dates intentionally omitted — sequence and dependencies only; the team sets dates at inception.
No code | This is a planning artifact. No implementation code is included or implied by it.
How to use | Fill the Status column on the Work Plan (dropdown). Record inception decisions on the Decision Record sheet before starting WP2. Track measures on Acceptance Targets.
Roles | Sponsor · Architecture lead · Data architect · Domain SME / data steward · Privacy steward · Platform owner · Evaluation owner · Data engineer · ML/agent engineer
Design refs | D-xx = design decisions and §x = sections of Architecture Design v0.2; B§x / B-Tx = sections / tables of the Pilot Blueprint v0.1.
Environment | Databricks FREE EDITION — learning/feasibility MVP only, non-commercial use per Databricks terms. Synthetic or open sample data only; no client data, no licensed COTS documentation. See the Free Edition Fit sheet for constraints and what is deferred to the customer environment at scale-up.

## Work Plan
Task ID | Work Package | Task | Description / key activities | Owner (role) | Supporting | Depends on | Deliverable | Exit / acceptance criteria | Design ref | Status
1.1 | WP1 · Inception & controls | Run inception workshop | Convene sponsor, architecture lead, data architect, stewards, platform owner; walk through blueprint decisions table; initiate the pilot decision record. | Architecture lead | All roles | — | Workshop record; decision record initiated | All six blueprint decisions have named owners and target dates | B§2
1.2 | WP1 · Inception & controls | Record source boundary decision | Select source system, product/module/version, candidate objects, domain/LOB, and explicit exclusions. | Data architect | Domain SME | 1.1 | Source boundary entry in decision record | Boundary is specific enough to enumerate candidate objects | B-T2; R-01/R-02
1.3 | WP1 · Inception & controls | Build source-object inventory & evidence-classification matrix | Enumerate in-scope objects; classify available evidence per object (metadata, profiles, samples) and mark approved evidence classes. First build artifact per blueprint §11. ¦ FREE EDITION: keep inventory small (10-30 objects); use synthetic or open sample data only — no client or licensed data. | Data architect | Privacy steward | 1.2 | Source-object inventory + evidence-classification matrix | Every in-scope object has an evidence classification | B§11
1.4 | WP1 · Inception & controls | Record evidence boundary decision | Approve allowed metadata, profile types, sample classes, sanitization rules, and retention period; define purge/archival procedure before any value-level evidence is collected. | Privacy steward | Platform owner | 1.3 | Evidence boundary entry in decision record; retention procedure | No value-level evidence class remains unclassified | D-11; B-T10
1.5 | WP1 · Inception & controls | Define approval model | Name the data architect, domain SME/steward, and privacy steward reviewers; set decision turnaround targets per artifact type. | Architecture lead | Sponsor | 1.1 | Approval model entry in decision record | Named individuals (not roles only) with turnaround targets | B-T2; §13.1
1.6 | WP1 · Inception & controls | Define confidence policy | Specify score components (retrieval fitness, pattern strength, COTS match, rule consistency, reviewer calibration), thresholds, calibration-set definition, and mandatory-review cases (identifiers, financial measures, privacy classes, ontology extensions, contradictions). | Architecture lead | Evaluation owner | 1.1 | Confidence policy entry in decision record | Thresholds and mandatory-review list signed off | D-09; B§7; B-T9
1.7 | WP1 · Inception & controls | Decide pilot operating model | Choose scheduled batch, event-driven workflow, or request/response entry point for the pilot (resolves open decision R-08). | Platform owner | Architecture lead | 1.1 | Operating model entry in decision record | One topology selected and recorded | R-08; B-T2
1.8 | WP1 · Inception & controls | Set success targets | Set quality, cost, latency, reviewer-throughput, and evidence-completeness thresholds; seed the Acceptance Targets sheet. ¦ FREE EDITION: cost/latency targets are indicative only under fair-usage quotas; real baselines set at scale-up. | Sponsor | Evaluation owner | 1.1 | Success-target entry; Acceptance Targets sheet populated | Targets measurable and owned | B-T12; §19.4
1.9 | WP1 · Inception & controls | Author tool-access policy | Define per-agent tool allowlists (read/query/retrieval only) and least-privilege service identities; document that write/deploy/execute/credential/ingest tools are absent and auditable. ¦ FREE EDITION: no account-level APIs/SCIM — per-agent service principals not feasible. Author the policy; enforce via code-level tool binding + UC grants under one identity. Full identity enforcement deferred to scale-up. | Architecture lead | Platform owner | 1.5 | Tool-access policy document | Policy covers all 7 agents; auditability path defined | D-08; B-T4
1.10 | WP1 · Inception & controls | Design engagement isolation | Design engagement-specific Unity Catalog catalogs/schemas, scoped service identities, retrieval collections, and isolated audit records. ¦ FREE EDITION: one workspace, one metastore — isolation reduces to schema-level separation in a single catalog. Concurrent-engagement isolation is designed on paper, demonstrated at scale-up. | Platform owner | Data engineer | 1.9 | Isolation design note | Design supports concurrent engagements without cross-access | D-12; B-T10
1.11 | WP1 · Inception & controls | GATE — Approve pilot boundary & controls | Sponsor reviews the signed pilot scope, evidence classification, named reviewers, success targets, and tool-access policy. | Sponsor | Architecture lead | 1.2–1.10 | Signed pilot decision record | WP1 exit: pilot boundary and controls approved | B-T11 WP1
2.1 | WP2 · Knowledge & repository foundation | Provision engagement environment | Create engagement UC catalog/schemas, service identities, grants, and audit configuration per the isolation design. ¦ FREE EDITION: provision schemas within the single catalog under the workspace identity. | Platform owner | Data engineer | 1.11 | Provisioned engagement environment | Identities hold only read/query/retrieval grants | D-08/D-12
2.2 | WP2 · Knowledge & repository foundation | Load & version knowledge packs | Place approved ontology, authorized COTS documentation (product/module/version-specific), enterprise standards, glossaries, and prior approved decisions into governed UC storage as versioned packs. ¦ FREE EDITION: outbound internet restricted — load packs by manual upload. Use open/synthetic P&C reference content, not licensed COTS documentation. | Domain SME / steward | Data engineer | 2.1 | Versioned ontology/COTS/standards packs | Each pack has version, owner, and authorization evidence | D-02; B-T11 WP2
2.3 | WP2 · Knowledge & repository foundation | Build scoped retrieval indexes | Create Vector Search indexes over approved documentation and sanitized metadata only, with mandatory filters: engagement, product version, domain/LOB, artifact type, approval state. ¦ FREE EDITION: one AI Search endpoint (one search unit), no Direct Vector Access — scoped collections become logical metadata filters on shared indexes. | Data engineer | ML/agent engineer | 2.2 | Scoped, filtered retrieval collections | Filter dimensions enforced on every query; no raw PII indexed | §19.3; D-11
2.4 | WP2 · Knowledge & repository foundation | Implement recommendation repository schema | Create Delta schemas for recommendation artifacts including the data-dictionary field groups: identity/scope, physical observation, semantic proposal, trust & evidence, governance, lineage. | Data engineer | Data architect | 2.1 | Recommendation repository (Delta) schema | Schema covers all six field groups of B-T6 | B-T6; §12
2.5 | WP2 · Knowledge & repository foundation | Implement review-state model | Implement trust states (Proposed / Needs clarification / Reviewed / Approved / Rejected / Superseded) and permitted transitions; decisions never overwrite prior versions. | Data engineer | Architecture lead | 2.4 | Review-state model in repository | State transitions match B-T7; versioning verified | §13.2; B-T7
2.6 | WP2 · Knowledge & repository foundation | Stand up prompt registry & output contracts | Register versioned agent system prompts and machine-reviewable output contracts (observation catalog, dictionary, ontology mapping, Silver, Gold, STTM, trust assessment) — the procedural memory baseline. | ML/agent engineer | Architecture lead | 2.1 | MLflow prompt registry + contract definitions | Every agent has a versioned prompt and output contract | §9; procedural memory
2.7 | WP2 · Knowledge & repository foundation | Create workflow-state & decision-memory tables | Create run/task-state tables (run ID, scope version, idempotency key, task states) and decision/approval record tables — the episodic memory baseline. | Data engineer | Platform owner | 2.4 | Workflow-state and decision tables | Supports B-T7 state transitions and reuse of approved decisions | D-10; episodic memory
2.8 | WP2 · Knowledge & repository foundation | Build context engineering component | Implement scope resolver, governed retrieval, evidence sanitization, context assembler, and context evaluation per the architecture; package includes objective, constraints, evidence, prior decisions, output contract, confidence rules. | ML/agent engineer | Data engineer | 2.3, 2.6, 2.7 | Context engineering component | Packages record all knowledge versions used | §9
2.9 | WP2 · Knowledge & repository foundation | GATE — Context reproducibility test | Assemble the same scoped context package twice from identical inputs; verify identical content and recorded versions. | Evaluation owner | ML/agent engineer | 2.8 | Reproducibility test record | WP2 exit: a scoped context package can be assembled reproducibly | B-T11 WP2
3.1 | WP3 · Source Intelligence MVP | Build read-only metadata query set | Implement governed queries over Unity Catalog information schema for schemas, tables, columns, types, keys, and constraints for in-scope objects. | Data engineer | Platform owner | 2.1 | Metadata query set | Read-only; covers all inventory objects | B-T5
3.2 | WP3 · Source Intelligence MVP | Build governed profiling query set | Implement approved profiling queries (null rates, distincts, distributions, masked representative values) restricted to approved evidence classes with sanitization applied. ¦ FREE EDITION: single 2X-Small SQL warehouse shared with the workbench — batch profiling queries; keep object count small. | Data engineer | Privacy steward | 3.1, 1.4 | Profiling query set + sanitization checks | Only approved evidence classes retrievable | D-11; B-T10
3.3 | WP3 · Source Intelligence MVP | Implement Source Intelligence agent | Bind the agent to its allowlisted tools (metadata reader, profiling queries, COTS retrieval, relationship inference, lineage reader) with its contract: inspect, group, recognize COTS patterns, detect customizations, classify observed/inferred/unresolved. | ML/agent engineer | Data architect | 2.8, 3.1, 3.2 | Source Intelligence agent (pilot build) | Contract behaviors per B-T5 demonstrated on sample objects | B§4; B-T5
3.4 | WP3 · Source Intelligence MVP | Generate observation catalog & proposed data dictionary | Run the agent over the inventory; produce the observation catalog, proposed data dictionary (all B-T6 field groups), recognition assessment, and custom-extension register. | ML/agent engineer | Data architect | 3.3 | Observation catalog + proposed dictionary artifacts | Physical facts separated from semantic proposals on every entry | B§5; B-T6
3.5 | WP3 · Source Intelligence MVP | Implement confidence component scoring | Build the deterministic confidence calculator (retrieval fitness, pattern strength, COTS match, rule consistency, reviewer calibration) storing aggregate + component scores with reasons; LLM may explain, never self-certify. | Evaluation owner | ML/agent engineer | 1.6, 3.4 | Confidence scoring service + stored component scores | Component scores and routing effects recorded per B-T9 | D-09; B-T9
3.6 | WP3 · Source Intelligence MVP | Build reviewer queue & workbench MVP | Deliver the review interface over the repository: reviewers can accept, modify, reject, or defer dictionary entries with rationale capture and decision records. ¦ FREE EDITION: build as a Databricks App (max 3 per account; auto-stops after 24h, restart as needed). | Data engineer | Architecture lead | 2.5 | Review workbench MVP + reviewer queue | All four decision actions work and are versioned | B-T11 WP3; R-05
3.7 | WP3 · Source Intelligence MVP | Implement escalation routing | Route missing/contradictory evidence, low-confidence semantics, unknown identifiers, and potential privacy issues to the named reviewer; apply mandatory-review cases from the confidence policy. | ML/agent engineer | Evaluation owner | 3.5, 3.6 | Routing rules in workflow | Mandatory-review cases cannot bypass a named reviewer | B§7
3.8 | WP3 · Source Intelligence MVP | GATE — Reviewed source dictionary | Run the pilot scope end-to-end through Source Intelligence; reviewers process the dictionary entries; capture decisions and effort. | Data architect | All reviewers | 3.4–3.7 | Reviewed dictionary + reviewer-decision data | WP3 exit: reviewers can accept, modify, reject, or defer entries | B-T11 WP3
4.1 | WP4 · Modeling & mapping MVP | Implement Ontology & Semantic agent | Map dictionary concepts to the standard ontology; propose specializations/extensions with lifecycle states; rejections from episodic memory block re-proposals. | ML/agent engineer | Domain SME / steward | 3.8 | Ontology mapping package (pilot objects) | Lifecycle state on every mapping; unresolved marked, not guessed | D-01; §6
4.2 | WP4 · Modeling & mapping MVP | Implement Silver ODS Modeling agent | Recommend canonical entities, attributes, keys, relationships, history treatment, lineage, and privacy-class proposals against enterprise Silver standards. | ML/agent engineer | Data architect | 4.1 | Silver ODS recommendation (pilot domain) | Structure recommendations only — no DDL | D-04; §8
4.3 | WP4 · Modeling & mapping MVP | Implement Gold Data Product Modeling agent | Recommend facts, dimensions, grain, measures, conformed dimensions, and derived attributes traceable to rules, from the Silver proposal. | ML/agent engineer | Data architect | 4.2 | Gold model / data-product recommendation | Derived attributes trace to approved or explicitly inferred rules | §8
4.4 | WP4 · Modeling & mapping MVP | Implement STTM & Business-Rule agent | Produce Bronze→Silver and Silver→Gold STTM records (full minimum-record contract) and the business-rule catalog separating approved from inferred rules. | ML/agent engineer | Domain SME / steward | 4.2, 4.3 | STTM package + business-rule catalog | Every record carries evidence, confidence, assumptions, governance fields | §12.1
4.5 | WP4 · Modeling & mapping MVP | Implement Trust & Review agent | Build evidence/completeness evaluator, contradiction detector, and review router over all artifacts; connect to confidence scoring and the reviewer queue. | ML/agent engineer | Evaluation owner | 3.5, 3.6 | Trust assessment capability | Routes exceptions to named reviewers; cannot approve | §8; D-09
4.6 | WP4 · Modeling & mapping MVP | Implement orchestrator workflow | Build the durable workflow (chosen operating model from 1.7): immutable run IDs and scope versions, idempotency keys, bounded retries, targeted downstream invalidation on rejection or new evidence. ¦ FREE EDITION: max 5 concurrent job tasks — design the workflow sequential (fits the agent pipeline). | ML/agent engineer | Platform owner | 2.7, 1.7 | Durable orchestration (Lakeflow) for all agent tasks | Repeated identical request returns the same run artifact (B-T8) | D-10; B§6; B-T7/T8
4.7 | WP4 · Modeling & mapping MVP | Run recovery & invalidation tests | Controlled scenarios: transient failure retry, needs-clarification routing, reviewer rejection invalidating only dependent artifacts, unrelated approvals untouched. | Evaluation owner | ML/agent engineer | 4.6 | Recovery test results | All B-T7 transitions demonstrated | B§6; §19.2
4.8 | WP4 · Modeling & mapping MVP | GATE — End-to-end recommendation package | Execute a full run for the pilot scope producing dictionary, ontology mappings, Silver, Gold, STTM, and trust assessment for reviewer sign-off. | Architecture lead | All reviewers | 4.1–4.7 | End-to-end recommendation package | WP4 exit: end-to-end package is reviewable | B-T11 WP4
5.1 | WP5 · Evaluation & decision | Build labelled reviewer-decision set | Curate reviewer decisions from WP3/WP4 into a labelled test set for mapping quality and confidence calibration. | Evaluation owner | Domain SME / steward | 3.8 | Labelled test set | Coverage across artifact types and confidence bands | §19.1; B-T11 WP5
5.2 | WP5 · Evaluation & decision | Build evaluation datasets & judges | Create MLflow evaluation runs per agent: mapping precision/recall, evidence completeness, contract conformance, override rates. | Evaluation owner | ML/agent engineer | 5.1 | Per-agent evaluation suite | Metrics reproducible per release | §14 MLflow
5.3 | WP5 · Evaluation & decision | Calibrate confidence & set thresholds | Evaluate the confidence method against the labelled set; recalibrate components; fix progression/review thresholds for the pilot report. | Evaluation owner | Architecture lead | 5.2, 3.5 | Calibration report + final thresholds | Observed error rates within agreed drift bounds | D-09; §19.1
5.4 | WP5 · Evaluation & decision | Build metrics dashboard | Dashboard over the repository and run tables reporting every Acceptance Targets measure by source, domain, product/module/version. | Data engineer | Evaluation owner | 2.4 | Metrics dashboard (Databricks SQL) | All B-T12 measures visible | B-T12
5.5 | WP5 · Evaluation & decision | Measure cost & latency | Measure cost and elapsed time per source object by workflow stage; record failed/retried task rates. ¦ FREE EDITION: findings are indicative only; do not extrapolate cost/latency to production. Re-baseline at scale-up. | Platform owner | Evaluation owner | 4.8 | Cost/latency findings | Reported by stage against 1.8 targets | B-T12
5.6 | WP5 · Evaluation & decision | Run acceptance evaluation | Assess results against all first-release targets: evidence completeness 100%, sensitive-evidence compliance 100%, mapping quality, review throughput, workflow reliability, cost/latency. | Evaluation owner | Architecture lead | 5.3, 5.4, 5.5 | Acceptance evaluation report | Every target has a measured result and gap analysis | B-T12; §19.4
5.7 | WP5 · Evaluation & decision | GATE — Go/no-go decision | Present findings and recommendation; sponsor records the go/no-go decision with evidence; capture lessons and production-path considerations. | Sponsor | Architecture lead | 5.6 | Recorded sponsor decision + evidence | WP5 exit: sponsor decision recorded with evidence | B-T11 WP5

## Decision Record
Decision | Owner | What to record (per blueprint) | Linked task | Status | Decision recorded
Source boundary | Data architect | Source system, product/module/version, candidate objects, domain/LOB, and exclusions. | 1.2
Evidence boundary | Privacy steward + platform owner | Allowed metadata, profiles, sample classes, sanitization rules, and retention period. | 1.4
Approval model | Architecture lead | Named architect, domain SME/steward, privacy steward, and decision turnaround target. | 1.5
Confidence policy | Architecture lead + evaluation owner | Score components, calibration set, review thresholds, and mandatory-review cases. | 1.6
Operating model | Platform owner | Scheduled batch, event-driven workflow, or request/response entry point for the pilot. | 1.7
Success targets | Sponsor | Quality, cost, latency, reviewer-throughput, and evidence-completeness thresholds. | 1.8
Success targets | Sponsor | Quality, cost, latency, reviewer-throughput, and evidence-completeness thresholds. | 1.8

## Acceptance Targets
Measure | Definition | Target | Measured by | Owner | Result
Evidence completeness | Material recommendations including evidence, provenance, assumptions, contradictions, confidence reasons, and approval state. | 100% | Metrics dashboard (task 5.4) | Evaluation owner
Sensitive-evidence compliance | Retrieved/indexed inputs passing approved evidence-classification and sanitization controls. | 100% | Sanitization checks (3.2) + audit | Privacy steward
Mapping quality | Precision, recall, and reviewer override rate vs labelled reviewer set. | Threshold set at inception (1.8), before build | Evaluation suite (5.2) | Evaluation owner
Review throughput | Median elapsed time from recommendation creation to final reviewer decision; bottlenecks by role and artifact type. | Target set at inception (1.8) | Workbench decision records | Architecture lead
Workflow reliability | All task failures traceable; retry and invalidation behavior demonstrated in controlled scenarios. | Demonstrated (4.7) | Recovery tests + run tables | Platform owner
Cost and latency | Cost and elapsed time per source object by workflow stage; failed/retried task rate. FREE EDITION: indicative only. | Budget/SLA set at inception (1.8) | Cost/latency measurement (5.5) | Platform owner

## Free Edition Fit
Constraint | Free Edition limit (docs, Jun 2026) | MVP approach | Deferred to customer environment | Affected tasks
Usage terms | Non-commercial use only; no SLA or support. | Learning/feasibility build with synthetic or open sample data only. | Real client engagement runs in the customer's (trial or paid) workspace. | All
Workspace & metastore | One workspace, one metastore; no account console or account-level APIs. | Schema-level separation inside a single catalog. | True engagement isolation via separate catalogs/workspaces (D-12). | 1.10, 2.1
Service identities | No SSO/SCIM; account-level APIs unavailable - per-agent service principals impractical. | Enforce D-08 via code-level tool binding + UC grants under one identity; author the full policy anyway. | Least-privilege service principal per agent with auditable absence of write/deploy/ingest grants. | 1.9
Vector / AI Search | One AI Search endpoint, one search unit; no Direct Vector Access. | Single shared endpoint; scope via mandatory logical filters (engagement, version, domain/LOB, artifact type, approval state). | Physically scoped retrieval collections per engagement. | 2.3
Jobs / orchestration | Max 5 concurrent job tasks per account. | Sequential Lakeflow workflow - matches the agent pipeline order. | Parallel task fan-out across domains/objects. | 4.6
Model serving | Limited active endpoints; no provisioned throughput or GPU serving; certain models unavailable. | One shared pay-per-token FM endpoint for all 7 logical agents (matches assumption A1). | Model choice per agent role (R-07), provisioned throughput if needed. | All agent tasks
SQL warehouse | One 2X-Small warehouse. | Shared by profiling, dashboard, and workbench; keep inventory to 10-30 objects; batch profiling. | Dedicated warehouses; production-scale profiling. | 3.1, 3.2, 5.4, 3.6
Databricks Apps | Max 3 apps; auto-stop after 24h. | Review workbench as one App; restart when needed. | Continuously available workbench with SSO. | 3.6
Outbound internet | Restricted to trusted domains. | Manual upload of knowledge packs (open/synthetic P&C content). | Governed ingestion of licensed COTS documentation. | 2.2
Fair usage quotas | Compute can shut down for the rest of the day/month when quota is exceeded. | Treat cost/latency measures as indicative; schedule runs to stay under quota. | Real cost/latency baselines and budgets (B-T12). | 5.5, 1.8
Knowledge content | No licensed COTS models may be used in a non-commercial learning build. | Substitute open/synthetic COTS-like reference structures to exercise the recognition flow. | Authorized, version-specific COTS documentation (D-02). | 2.2, 3.3